## Project Overview
Quest | XP | Progress | Scope | Adventurer(s) | Notes | Start Date | End Date
Installing regular house cleaners | Intermediate | Initiating | House | Mark | Look over options and consult house | 2025-01-01
Cleaning Party | Low | Initiating | House | House | January - 25th, 26th, 30th | 2025-01-12
Spring, 2025 Party | Intermediate | Initiating | House | House | March 29th | 2025-01-12
Installing new fridge | High | Launched | House | Mark |  |  | 2025-01-01
Interum Coordination | High | Launched | House | Mark | Need to run through list and communicate to volunteers. | 2024-07-20 | 2024-10-01
Poduce Meal System for Fall | High | Launched | Finance | Mark |  | 2024-08-11 | 2024-09-08
Replace Carbon Mon. Alarm | High | Launched | Facilities | Mark + Lua |  | 2024-08-11 | 2024-09-08
Officer Roles Presentation & Poster | Intermediate | Launched | Education | Mark | RACI chart not necessary. Print out details sheet. | 2024-08-11 | 2024-08-25
Document Apollo Account Info | Intermediate | Launched | House | Mark |  | 2024-08-11 | 2024-09-08
Potluck | Low | Launched | House | Luca + House |  | 2024-09-21 | 2024-09-21
Repainting | Intermediate | Not Started | House
Caulking Everything | Intermediate | Not Started | House
Upgrading House Wifi | Intermediate | Not Started
Apollo Goals Presentation | Low | Not Started | Education | Mark
Preventative Maintenance Cleaning | Low | Not Started | Facilities | Abbie C. + Mark
Online LBWL Account | Low | Not Started | Finance | Mark + Treasurer
Analyze Utility Trends | Low | Not Started | Finance | Mark
Merge Parking Account | Low | Not Started | Finance | Mark
Reviving Pot & Pans | Low | Not Started | House
Smoothing Pavement Lump | Low | Not Started | House
Update Water System | Low | Not Started | House
Demolding Bathrooms | High | Ongoing | House | Everyone | Encourage members more | 2024-07-01
Replace Keys | High | Ongoing | Facilities | Mark + Abbie C. | Gotta do ourselves | 2024-08-01
Create Apollo PM Constitution | Intermediate | Ongoing | House | Mark
House Metrics | Intermediate | Ongoing | House | Mark
Replacing Window Screens | Intermediate | Ongoing | Facilities | Mark + Abbie C. | SHC is on it. | 2024-07-01
Analyze Bank Account Trends | Intermediate | Ongoing | Finance | Mark
Replace Bathroom D towel rack | Low | Ongoing | House | Mark
Install point-based chore system | High | Ongoing | Task Master | Mark + Abbi S.
Standardized Fine List | Intermediate | Paused | House
Garden/Lawn Maintenance | Intermediate | Paused | House
Take Basement Inventory | Intermediate | Paused | House | Mark
Redo Bathrooms | Intermediate | Paused | Facilities |  | SHC retiled bathroom D
Upgrade Dirty Dish System | Intermediate | Paused | House | Mark | Tub upgrade | 2024-07-15
Redo Floors | Intermediate | Paused | House | Mark | R4 + R14 Done | 2024-07-22
Ensure Fire Safety | Intermediate | Paused | Facilities | Maria
Bike + Rack Restoration | Low | Paused | House | Lua | Some repairs were made and weeds cleared | 2024-07-21
Dryer Vents + WM Filter | Low | Paused | Facilities |  |  | 2024-07-01